## Basic Template
				Project:		All Our Photos					Date: 01/01/2010
				Project Objective: To develop two demo levels of the Tank Game

Objectives					Major Tasks			Project Completed By: 04/3/2010					Owner
O				1	Storyboards completed			O					A	B	B	B
O				2	Gameplay, UI, powerups, feature set defined				O					A	B	B	B
	O			3	Initial placeholder graphical asset created					O					A
	O			4	Mid semester graphical asset created					O					A
		O		5	Final graphical asset created					O					A
	O			6	Initial placeholder audio asset created					O					A
	O			7	Mid semester audio assets completed					O					A
		O		8	Final audio assets created					O					A
	O	O		9	Main game finite state machine created					O					A
	O	O		10	Main tank finite state machine created					O					A
	O	O		11	Initial user interface created					O					A
		O		12	Final user interface created					O					A
		O		13	Bullets finite state machine created					O					A
		O		14	Enemy finite state machine and AI created					O					A
				15	MIDTERM DEMO					O					A	B	B	B
		O		16	Powerup 1 completed					O					A
		O		17	Powerup 2 completed					O					A
		O		18	Second game level completed					O					A
		O		19	Score board implemented					O					A
		O		20	Boss implemented					O					A
			O	21	Playtesting among developers					O	O				O				A	B	B	B
			O	22	Playtest with friends and gameplay tweaked					O					O			A
			O	23	Schedule playtest with friends				O					O					A
	O			24	Midterm powerpoint completed					O					A
		O		25	Final powerpoint completed					O			A
	O	O	O	26	Regular demo integrated					O	O	O	O	O	O	O			A	B
	O	O		27	Web site updated					O		O		O		O		O		A	B
		O		28	FINAL DEMO					O	A	B	B	B
	O	O		29	Demo rehearsals					O					O			A	B	B	B
				# People working on the project:
Create design	Build Midterm Demo	Final Demo	Playtest and tune		Major Tasks	Target Dates		02/12	02/19	02/26	03/05	03/12	03/19	03/26	04/02	04/09	04/16	04/30	05/07	Homer Simpson	Peter Griffin	Al Bundy	Philip Fry

				Objectives

				Key
				O	expected task activity here					A = primary owner
				O	no progress or stuck					B = secondary owner
				O	in progress
				O	completed
				Summary & Forecast

				Version 03/19/2010 of the OPPM sheet

Adapted from OPPM: www.onepageprojectmanager.com